## Budget
Budget Code | Original Budget | Budget Modifications | Projected Budget | Approved Changes | Contract Change Orders | Revised Budget | Pending Budget | Commitments | Pending Costs | Direct Costs | Projected Costs | Forecast to Complete | Projected Over/Under | Committed Invoiced Amount | Actual Amount | Commitment Change Orders
013120 - Vice President - Labor | 60945 | 0 | 60945 | 0 | 0 | 60945 | 0 | 0 | 0 | 0 | 0 | 60945 | 0 | 0 | 0 | 0
013126 - Pre-construction - Expense | 49356 | 0 | 49356 | 0 | 0 | 49356 | 0 | 0 | 0 | 0 | 0 | 49356 | 0 | 0 | 0 | 0
013127 - Sr. Project Manager - Labor | 63983 | 0 | 63983 | 0 | 0 | 63983 | 0 | 0 | 0 | 0 | 0 | 63983 | 0 | 0 | 0 | 0
013128 - Project Manager - Labor | 152340 | 0 | 152340 | 0 | 0 | 152340 | 0 | 0 | 0 | 0 | 0 | 152340 | 0 | 0 | 0 | 0
013130 - Project Engineer - Labor | 54847 | 0 | 54847 | 0 | 0 | 54847 | 0 | 0 | 0 | 0 | 0 | 54847 | 0 | 0 | 0 | 0
013132 - Intern - Labor | 29255 | 0 | 29255 | 0 | 0 | 29255 | 0 | 0 | 0 | 0 | 0 | 29255 | 0 | 0 | 0 | 0
013223 - Construction Layout - Expense | 1500 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0
013236 - Aerial & Periodic Drones - Expense | 3500 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0
013238 - Jobsite Security - Expense | 3500 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0
013245 - Office Supplies - Expense | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 167.99 | 167.99 | 4832.01 | 0 | 0 | 167.99 | 0
013247 - Printing & Copying - Expense | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0
013249 - Postage & Courier - Expense | 7500 | 0 | 7500 | 0 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 7500 | 0 | 0 | 0 | 0
014126 - Permit Requirements - Expense | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.1 | 0
015113 - Temporary Electric - Expense | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0
015119 - Temporary Fuel - Expense | 1500 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0
015133 - Temporary Internet/Telecomm - Expense | 2500 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 382.15 | 382.15 | 2117.85 | 0 | 0 | 382.15 | 0
015213 - Field Offices - Expense | 20000 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0
015216 - First Aid / Safety Supplies - Expense | 3500 | 0 | 3500 | 0 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 3500 | 0 | 0 | 0 | 0
015219 - Temporary Toilets - Expense | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
015519 - Temporary Parking Areas - Expense | 20339 | 0 | 20339 | 0 | 0 | 20339 | 0 | 0 | 0 | 0 | 0 | 20339 | 0 | 0 | 0 | 0
015626 - Tempoary Fencing - Subcontract | 25000 | 0 | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
015713 - Temporary Erosion and Sediment - Subcontract | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0
015813 - Temporary Project Signage - Expense | 1500 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0
016113 - Software Licensing - Expense | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
016500 - Travel & Entertainment - Expense | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 814.53 | 814.53 | 49185.47 | 0 | 0 | 814.53 | 0
016502 - Truck Allowance - Expense | 15000 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0
016503 - Truck Fuel - Expense | 9000 | 0 | 9000 | 0 | 0 | 9000 | 0 | 0 | 0 | 0 | 0 | 9000 | 0 | 0 | 0 | 0
016505 - Marketing - Expense | 2500 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 164.56 | 164.56 | 2335.44 | 0 | 0 | 164.56 | 0
017123 - Construction Surveying - Subcontract | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
017333 - Misc Small Tools - Expense | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0
017336 - Equipment Rental - Expense | 12000 | 0 | 12000 | 0 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 12000 | 0 | 0 | 0 | 0
017413 - Progress Cleaning - Subcontract | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
017419 - Dumpsters - Expense | 21250 | 0 | 21250 | 0 | 0 | 21250 | 0 | 0 | 0 | 0 | 0 | 21250 | 0 | 0 | 0 | 0
017423 - Final Cleaning - Subcontract | 25000 | 0 | 25000 | 0 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 25000 | 0 | 0 | 0 | 0
017425 - General Labor - Expense | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
033000 - Cast-in-Place Concrete - Subcontract | 1575000 | 0 | 1575000 | 0 | 0 | 1575000 | 0 | 0 | 1001554 | 0 | 1001554 | 573446 | 0 | 0 | 0 | 0
034100 - Precast Structural Concrete - Subcontract | 1175720 | 0 | 1175720 | 0 | 0 | 1175720 | 0 | 0 | 1095100 | 0 | 1095100 | 80620 | 0 | 0 | 0 | 0
042200 - Concrete Unit Masonry-Block - Subcontract | 350000 | 0 | 350000 | 0 | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 350000 | 0 | 0 | 0 | 0
051200 - Structural Steel Framing - Subcontract | 1443720 | 0 | 1443720 | 0 | 0 | 1443720 | 0 | 0 | 1056250 | 0 | 1056250 | 387470 | 0 | 0 | 0 | 0
075400 - Thermoplastic Roofing (TPO) - Subcontract | 550000 | 0 | 550000 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 550000 | 0 | 0 | 0 | 0
078400 - Firestopping - Subcontract | 60000 | 0 | 60000 | 0 | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 60000 | 0 | 0 | 0 | 0
081113 - Hollow Metal Door and Frames - Subcontract | 30000 | 0 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
084300 - Storefronts - Subcontract | 40000 | 0 | 40000 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0
092116 - Gypsum Board Assemblies - Subcontract | 216200 | 0 | 216200 | 0 | 0 | 216200 | 0 | 0 | 0 | 0 | 0 | 216200 | 0 | 0 | 0 | 0
092216 - Non-Structural Metal Framing - Subcontract | 625000 | 0 | 625000 | 0 | 0 | 625000 | 0 | 0 | 0 | 0 | 0 | 625000 | 0 | 0 | 0 | 0
099113 - Exterior Painting - Subcontract | 113750 | 0 | 113750 | 0 | 0 | 113750 | 0 | 0 | 0 | 0 | 0 | 113750 | 0 | 0 | 0 | 0
101400 - Signage - Subcontract | 2500 | 0 | 2500 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 0 | 0 | 0
102813 - Toilet Accessories - Subcontract | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
104116 - Knox Box - Subcontract | 1500 | 0 | 1500 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0
104416 - Fire Extinguishers - Subcontract | 5000 | 0 | 5000 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0
107316 - Canopies - Subcontract | 15000 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0
111300 - Loading Dock Equipment - Subcontract | 238274 | 0 | 238274 | 0 | 0 | 238274 | 0 | 0 | 0 | 0 | 0 | 238274 | 0 | 0 | 0 | 0
211316 - Dry-Pipe Sprinkler Systems - Subcontract | 503000 | 0 | 503000 | 0 | 0 | 503000 | 0 | 0 | 0 | 0 | 0 | 503000 | 0 | 0 | 0 | 0
221000 - Plumbing Piping - Subcontract | 275000 | 0 | 275000 | 0 | 0 | 275000 | 0 | 0 | 0 | 0 | 0 | 275000 | 0 | 0 | 0 | 0
233000 - HVAC Air Distribution - Subcontract | 1000000 | 0 | 1000000 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0 | 0 | 1000000 | 0 | 0 | 0 | 0
237000 - Central HVAC Equipment - Material | 1300000 | 0 | 1300000 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0 | 0 | 1300000 | 0 | 0 | 0 | 0
261000 - Med-Volt Elect Distribution - Subcontract | 795000 | 0 | 795000 | 0 | 0 | 795000 | 0 | 0 | 0 | 0 | 0 | 795000 | 0 | 0 | 0 | 0
274000 - Fire Alarm & Life Safety Syst - Subcontract | 35000 | 0 | 35000 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0
312213 - Rough Grading - Subcontract | 318728 | 0 | 318728 | 0 | 0 | 318728 | 0 | 0 | 0 | 0 | 0 | 318728 | 0 | 0 | 0 | 0
313200 - Soil Stabilization - Subcontract | 225000 | 0 | 225000 | 0 | 0 | 225000 | 0 | 0 | 0 | 0 | 0 | 225000 | 0 | 0 | 0 | 0
321216 - Asphalt Paving - Subcontract | 375475 | 0 | 375475 | 0 | 0 | 375475 | 0 | 0 | 0 | 0 | 0 | 375475 | 0 | 0 | 0 | 0
321613 - Curbs and Gutters - Subcontract | 15000 | 0 | 15000 | 0 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 15000 | 0 | 0 | 0 | 0
321623 - Sidewalks - Subcontract | 20000 | 0 | 20000 | 0 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 | 0
321633 - Driveways - Subcontract | 30000 | 0 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
321723 - Pavement Markings - Subcontract | 10000 | 0 | 10000 | 0 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 0 | 0 | 0
323300 - Site Furnishings - Subcontract | 30000 | 0 | 30000 | 0 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 | 0
329000 - Planting - Subcontract | 65000 | 0 | 65000 | 0 | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 65000 | 0 | 0 | 0 | 0
502000 - Site Engineering - Subcontract | 75000 | 0 | 75000 | 0 | 0 | 75000 | 0 | 50500 | 0 | 0 | 50500 | 24500 | 0 | 0 | 0 | 0
505000 - Structural Engineering - Subcontract | 85000 | 0 | 85000 | 0 | 0 | 85000 | 0 | 0 | 0 | 0 | 0 | 85000 | 0 | 0 | 0 | 0
522000 - Architectural Services - Subcontract | 50000 | 0 | 50000 | 0 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 50000 | 0 | 0 | 0 | 0
550050 - Insurance - Subcontract | 166991 | 0 | 166991 | 0 | 0 | 166991 | 0 | 0 | 0 | 0 | 0 | 166991 | 0 | 0 | 0 | 0
550099 - Unallocated Costs - Subcontract | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550100 - Contingency - Subcontract | 618485 | 0 | 618485 | 0 | 0 | 618485 | 0 | 0 | 0 | 0 | 0 | 618485 | 0 | 0 | 0 | 0
550500 - Contractor Fee - Subcontract | 1403960 | 0 | 1403960 | 0 | 0 | 1403960 | 0 | 0 | 0 | 0 | 0 | 1403960 | 0 | 0 | 0 | 0
Grand Total: | 14559118 | 0 | 14559118 | 0 | 0 | 14559118 | 0 | 50500 | 3152904 | 1529.23 | 3204933.23 | 11354184.77 | 0 | 0 | 1540.33 | 0